## Sheet1
Week (starting 26/03 )
| 1 | 2 | 3 | 4 | 5 | 6 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Prelim. research period
Research details of chosen actuation/power/control methods
Review and finalise plans with supervisor. Alter if required.
Project lab work begins | bar: 11
Design robot morphology. Finalise with supervisor | bar: 11
Fabricate MFCs | bar: Week (starting 26/03 ) 12 to Week (starting 26/03 ) 13
Test MFC capabilities and ensure correct function | bar: Week (starting 26/03 ) 13 to Week (starting 26/03 ) 14
Fabricate actuators | bar: Week (starting 26/03 ) 14 to Week (starting 26/03 ) 16
Test actuator capabilities, ensure correct function | bar: Week (starting 26/03 ) 16 to Week (starting 26/03 ) 17
Fabricate full prototype | bar: Week (starting 26/03 ) 17 to Week (starting 26/03 ) 18
Test prototype capabilities | bar: Week (starting 26/03 ) 18 to Week (starting 26/03 ) 19
Dissertation write up | bar: Week (starting 26/03 ) 20 to Week (starting 26/03 ) 22